## SCORING MATRIX
CONSEQUENCE
LIKELIHOOD ↓ | INSIGNIFICANT | MINOR | MODERATE | MAJOR | CATASTROPHIC
| 1 | 2 | 3 | 4 | 5
ALMOST | 5 | 10 | 15 | 20 | 25
CERTAIN 5
| 4 | 8 | 12 | 16 | 20
LIKELY 4
| 3 | 6 | 9 | 12 | 15
POSSIBLE 3
| 2 | 4 | 6 | 8 | 10
UNLIKELY 2
| 1 | 2 | 3 | 4 | 5
RARE 1
High Risk
(15 to 25)
Medium Risk
(5 to 12)
Low Risk
(1 to 4)

## OVERVIEW
DOCUMENT 10
Risk Register | South Asian young Peoples Mental Health Project
Bidder Name:
Project Specific Risks
Risk No. | Risk Owner | Risk Handler | Risk Title | Risk Description | Likelihood | Impact | Rating | Mitigation Plan | Due Date | Actions taken to Deliver Mitigation | Review Date
1 | BEP |  | Young Peoples Engagement | The Project fails to engage the target cohort | 2 | 5 | 10 | The project is premised on consultation with young people and the consultation will continue through the life of the project.
2 | Parent workstream |  | Parent Engagement | The Project fails to engage parents and as a result elements of the project fail and the engagement of young people is impaired | 2 | 4 | 8 | the project is premised on consultation with parents and the consultation will continue through the life of the project.
3 | BEP |  | Community Engagement | The Community does not see the value of the services and as a result engagement is impaired. | 2 | 3 | 6 | Partners to the project and specifically the schools have the confidence of the community. The launch of the project will use the resources of the project co-ordinated via the governance structure.
4 | Delivery Group |  | Number of referrals made from schools exceeds capacity | schools identify a higher number of students who need mentoring which exceeds the allocated allowance, YP,s needs not addressed | 4 | 4 | 16 | Identifying CPD opprtunities for staff to further develop a culturally sensitive approach to supporting the targeted cohort and for schools to have a clear understanding of referral criteria. As relationships develop between school and community YP will be encouraged to access universal services
5 | Parent workstream |  | Number of parents exceed capacity | more parents requiring to particpate in programmes then allowence | 6 | 2 | 8 | start waiting list and priortise with school most suitable parents to attend, explore opportunities to amend work to use workshops in school to reach more parents and upskill school staff. Link to community through public health opportunities
6 | Parent workstream |  | number of Parent champions do not meet requirements | less parents volunteer to become parent champions | 9 | 6 | 15 | work with schools to identiyf and motivate parents.
7 | BEP |  | Number of referrals made from various sources may exceed capacity of emotional support provision | Combined referrals from young people parents and schools for young people previously unaware or unable to access services exceeds the level of provision | 3 | 4 | 12 | Through public health agenda communicate to key stakeholders the nature and level of take up to enable progression routes into existing services. Address level of provision in subsequent years of the project
8 | Emotional Support |  | Levels of complexity of referrals to emotional support higher than anticipated in modeling of service | A significant number of compound and or complex presentations being referred to the SAP eg young people showing indications of autism. | 3 | 4 | 12 | Through public health agenda communicate to key stakeholders the nature and level of take up to enable progression routes into existing services. Where possible address skills of providers of services through cPD or recruitment of more senior staff in subsequent years of the project
9 | BEP |  | Procurement of delivery partners | Ensuring quality and robustness of delivery partners to delivery programmes | 3 | 5 | 15 | BEP have experience of working with contracts and we have sought additional support through the Birmingham City Council Procurment team and also the CCG. Due diligence in terms of organisations' policies, procedures and processes will be undertaken.
10 | BEP |  | Performance of delivery partners | Suppliers commissioned to delivery elements of the programme may not performt o the levels required by their contract | 3 | 5 | 15 | The BEP team have experience of contract management. The Project Lead will hold regular contract reviews with delivery partners. This will sit entirely separately from the project's delivery group.
11 | BEP |  | Recruitment of Project Staff | Recruitment cannot take place until funding is agreed. Risk that appropriate staff are not identified | 2 | 5 | 10 | Job descriptions will be evaluated on receipt of funding and all programme management roles will be externally advertised as soon as possible once funding is confirmed.
12 | BEP |  | Changes in school arrangements | Risk of change in management for schools engaged in the programme | 2 | 5 | 10 | Schools have already been identified and relationships are being or have been established. BEP know from experience that relationships are key to implementation and success and we will ensure that schools are continually updated in relation to progress, process. outcomes and impact. Changes in school structure are known to BEP for the city. BEP have experience of managing this through the NewStart programme already in place
13 | BEP |  | Data sharing | Ensuring all data sharing protocols are in place | 2 | 5 | 10 | No personal data will be kept by BEP as the Lead organisation. Consent will be obtained by delivery partners from parents and young people where work will take place. Due diligence in procurement will ensure organisations are able to keep and store information safely
14 | BEP |  | Financial pressures across the city | Community based organisations across the city arfe facing significant financial challenges linked to funding reductions across the system. | 2 | 4 | 8 | BEP have explored opportunities with the Office of the Police and Crime Commissioner to work with us on sustainability. This bid will bring additional funds in to the city.

## CATEGORIES OF RISK DEFINITIONS
Strategic | arise from the vision and direction of an organisation
Operational | arise from the functional, operational and administrative procedures, people, premises and equipment
Financial | arise financially
Compliance | arise from the need to ensure compliance with laws, regulations and policy frameworks
Market | arise from factors or changes in the external supply market
Technological | arises from technology dynamism and obsolescence
Supply | arises from supply market instability and resource scarcity
Reputational | arising from exposure of unethical, socially irresponsible or environment damaging activity